## Product_Backlog
Product Name:
Team ID:

Name:	Jimmy Chen
Initials:	J.C.
Student ID:	1001213543

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	18
Sprint 1 Left	18
Sprint 2 Left	16
Sprint 3 Left	12

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Sprint #	As a...	I want to...	So that...	Notes
FID_01	1			PM	create robot parts	I can define robot models	No menu required here – run program, create a part
FID_02	2			PM	define new robot models	RRS can sell them to our Beloved Customers	Menu needed – create parts, then create a robot model
FID_03	3			BC	browse a catalog of robots	I can buy one or more robots	Need to list robots models, then list parts in selected model
FID_04	4			SA	create a robot order for a Customer	I can sell robots and thus do my job well	Select robot model and quantity, show details with total price
FID_05	5			PB	ensure persistence of the RRS data	we don't lose orders or historical data	Write the data to disk and reload it next time the program runs
FID_06	6			PB / SA	view a list of orders per SA	I can estimate the value of employees / / I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
FID_07	7			BC	view my orders	see what I have coming to me	Show list of orders for a BC with total price, then list details of selected order
FID_08	8			BC	view my bill	I can pay for my robots	Show a BC invoice. Actual payment is outside the scope of this project
FID_09	9			SA	view a sales report	I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
FID_10	10			PB	view a list of orders	I can manage the company	Show list of every order with total price, then list details of selected order
FID_11	11			SA	create a bulk (2+) robot order for a Customer	avoid proliferation of orders and paperwork	Allow more than one robot model (with respective quantity) on a single order
FID_12	12			PM	hide robot parts	obsolete parts aren't accidentally used	Mark robot parts as “obsolete” and don't allow adding them to new robot models
FID_013	13			PM	hide robot models	obsolete robots aren't ordered	Mark robot models as “obsolete” and don't allow adding them to new orders
FID_014	14			SA	save a draft order and return to it later	I can multi-task between indecisive customers	Save an order that hasn't been complete, and allow SA to resume work on it later
FID_15	15			PM	add custom pictures to robot models	BC are more likely to buy my robots	(Probably can't address until Homework #6)
FID_16	16			BC	see a pie chart of a model's component costs	I can decide if I want a different model	(Probably can't address until Homework #6)
FID_17	17			BC	browse and order robots over the web	I don't have to talk to the Sales Associates!	(Probably can't address until Homework #6)
FID_18	18			PB	avoid any delays in the RRS web software	my SA team is at maximum productivity	This likely means using threads for key processes / (Probably can't address until Homework #6)
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_1_Backlog
Sprint #	1
Start on	9/29/2016
End on	10/6/2016
Demo on	~

Total Tasks	6
Day 1 Left	6
Day 2 Left	6
Day 3 Left	5
Day 4 Left	3
Day 5 Left	3
Day 6 Left	2
Day 7 Left	1

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
TID_01	FID_01	Manufacturing		Jimmy	create robot parts	Design
TID_02	FID_02	Manufacturing		Jimmy	define new robot models	Design
TID_03	FID_03	POS		Jimmy	browse a catalog of robots	Design
TID_04	FID_04	POS		Jimmy	create a robot order for a Customer	Design
TID_05	FID_05	POS		Jimmy	ensure persistence of the RRS data	Design
TID_06	FID_06	POS		Jimmy	view a list of orders per SA	Design
Sprint Burn Chart
Days
Tasks

## Sprint_2_Backlog
Sprint #	2
Start on	10/6/2016
End on	10/13/2016
Demo on	~

Total Tasks	6
Day 1 Left	5
Day 2 Left	4
Day 3 Left	2
Day 4 Left	2
Day 5 Left	1
Day 6 Left	1
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
TID_01	FID_01	Manufacturing		Jimmy	create robot parts	Implementation
TID_02	FID_02	Manufacturing		Jimmy	define new robot models	Implementation
TID_03	FID_03	POS		Jimmy	browse a catalog of robots	Design
TID_04	FID_04	POS		Jimmy	create a robot order for a Customer	Design
TID_05	FID_05	POS		Jimmy	ensure persistence of the RRS data	Design
TID_06	FID_06	POS		Jimmy	view a list of orders per SA	Design
Sprint Burn Chart
Days
Tasks

## Sprint_3_Backlog
Sprint #	3
Start on	10/13/2016
End on	10/20/2016
Demo on	~

Total Tasks	4
Day 1 Left	4
Day 2 Left	3
Day 3 Left	3
Day 4 Left	2
Day 5 Left	2
Day 6 Left	1
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
TID_03	FID_03	POS		Jimmy	browse a catalog of robots	Implementation
TID_04	FID_04	POS		Jimmy	create a robot order for a Customer	Implementation
TID_05	FID_05	POS		Jimmy	ensure persistence of the RRS data	Implementation
TID_06	FID_06	POS		Jimmy	view a list of orders per SA	Implementation
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog
Sprint #					*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	23
Day 1 Left	22
Day 2 Left	19
Day 3 Left	15
Day 4 Left	15
Day 5 Left	9
Day 6 Left	4
Day 7 Left	1

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Days
Tasks